Memo to:    	SMH Board of Directors

From:  		Mary Burnett, Chair

Joint Child Care Task Force

Date:		August 2021

RE: 		Update on Proposed Merger with St. Peter’s Day Care (SPDC)

The Joint Task Force has met multiple times over the summer to address outstanding due diligence items.    Much progress has been made, largely aided by the support of our consultant, Daljit Garry. A draft Merger agreement has been developed and is under review by SPDC lawyers.  Draft communication pieces for both staff and parents have been developed.  Three key areas still under consideration:

- Licensing:  Review of site diagrams for SPDC and what, if any, capital changes may be required.

- Financial:  Identify costs to SMH in order to bring parity with regards to group benefits and pension plan of SPDC.

- “Tail” insurance for D&O at SPDC.

Due Diligence Items

| ST MATTHEW’S HOUSE | ST PETER’S | DIOCESE | OTHER/UNKNOWN |
| --- | --- | --- | --- |
| - Consolidated Operating Budget √ - Determine one time integration costs. (ongoing) - Determine financial obligations related to pensions √ - Seek municipal approvals from Fire Dept, Health Dept, Building Dept. zoning √ - Initiate licensing process with ministry, file legal papers, policies & procedures, seek approval for site and floor plans √ | - Determine costs related to any outstanding financial matters. √ - List of assets to be transferred. √ - Provide written confirmation on transfer of reserves√ - Provision of regular updates on the utilization of the reserves - Renewed Collective agreement√ - Clarity around payout of sick days √ | - Provide copy of lease detailing terms and costs √ - Provide details on support for capital improvements set out by the ministry √ | - Assigning of contracts √ - City Funding√ |